## READ ME
Requirements and Progress Tracking
Deliverable | A08-06 from the 2026-08-05 call: a tracking document kept SEPARATE from the Word proposal
For | Supervisor meeting Wednesday 2026-08-12, 09:00 (Iris, Arnon, Ali)
Source of truth | docs/research/meetings/2026-08-05-supervisor-meeting.md (canonical machine-derived record, E1-E15 + A08-01..09)
IMPORTANT | The 2026-08-05 record is machine-transcribed with INFERRED speakers and is pending participant confirmation. Nothing in this workbook is marked approved. 'Applied' means the correction was implemented in the drafts; it does not mean a supervisor signed it off.
Status vocabulary | Applied = correction implemented in the drafts ¦ Delivered = artefact exists in this package ¦ In progress = started, not finished ¦ Not started (instructed) = deliberately not begun per Iris's instruction ¦ Ali only = cannot be done by anyone else ¦ Supervisor decision = needs Iris/Arnon ¦ Blocked = external gate closed
Claim boundary | EXP-005 holds 0 of 24 required independent generalization-safe expert labels; 0 of 6 medical entry gates pass; literature searches QL-01-QL-05 are protocol-ready and NOT run. No accuracy, generalization, clinical-performance or effort-reduction claim is made anywhere.

## Aug-5 Requirements
Requirements from the 2026-08-05 supervision call (E1-E15)
Paraphrases of machine-generated Hebrew ASR with INFERRED speakers, pending participant confirmation. 'Applied' = implemented in the drafts, NOT supervisor-approved. E2/E3/E9(A08-09) informational rows omitted.
ID | Raised by | Requirement (paraphrase) | Timestamp | State | How it is addressed / what remains
E1 | Iris | Move from a statement of intentions to an actual thesis proposal; time is tight | 00:00:08-00:00:35 | In progress | Standing pressure; governs the whole package. v0.3 proposal + full Chapter 3 delivered this cycle.
E4 | Arnon | Draft conflates the Agentic-AI SOLUTION with the RESEARCH QUESTION; sharpen the split; cut padding | 00:11:01-00:13:07 | Applied | Chapter 3 rewritten as an open-question argument. Every gap paragraph cites literature or evidence, never VEGO-AI features. §3.9 states 'the question is the contribution, the platform is the vehicle'.
E5 | Iris | Remove 'reused' from the main RQ - reuse belongs in a sub-question | 00:13:39-00:15:09 | Applied | U-RQ carries no 'reused'; reuse lives in SQ2 (capture/govern) and SQ3 (transfer). NOTE: the proposal TITLE still contains it - D-TITLE-01 raised.
E6 | Iris | Narrow the main RQ explicitly to variability identification/classification | 00:15:10-00:17:23 | Applied | U-RQ narrowed to variability exploration in guideline operationalization scenarios. DISCREPANCY FLAGGED: record says 'identification/classification', reconstructed wording says 'exploration' - A08-01 must settle it.
E7 | Iris/Arnon/Ali | Keep 'reliable'; lean toward dropping 'auditable'/'transferable'/'end-to-end'; insert 'variability exploration scenarios' into SQ1 | 00:26:29-00:29:27 | Applied | Applied per the leaning; exact final text still needs the A08-01 saved-draft check.
E8 | Iris/Arnon | Split SQ2 into (a) what the expert says/how captured vs (b) how it transfers; 'expert' vs 'human' - leaning 'expert' | 00:29:27-00:36:29 | Applied | Capture-vs-transfer split is explicit in §3.6. 'Expert judgment' used in SQ2/SQ3. ASYMMETRY FLAGGED: U-RQ and SQ1 still say 'human judgment' - raised as a D-RQ-01 item rather than harmonised unilaterally.
E9 | Iris | Tie SQ2 explicitly to 'core reasoning'; add an evaluation-criteria clause in SQ1/SQ3 style | 00:41:31-00:44:02 | Applied | 'Including the system's core reasoning' is in the SQ2 wording AND argued in §3.6 prose. Evaluation criteria are built into all three sub-questions.
E10 | Iris | SQ3 wording 'looks good'; mild discomfort with 'transparently' | 00:39:20-00:41:00 | Applied | SQ3 wording kept. 'Transparently' currently sits in SQ2; retained with a flagged note for the final wording pass.
E11 | Iris | Start from the SE domain, not medical; Clalit chronic-pain vs Soroka AMD as maximally different examples | 00:37:19-00:39:20 | Applied | §3.7 uses exactly this contrast to justify a classification rather than a blanket transfer claim. SQ3 stays software/modelling-first.
E12 | Arnon | SQ3 must classify domain-specific vs broadly transferable uncertainty (actor/use-case failure = general capability gap) | 00:52:17-00:53:54 | Applied | Classification is the analytic core of §3.7. The actor/use-case example is stated as a CANDIDATE hypothesis to test, not as an established fact.
E13 | Iris | Confirmed chapter structure: Intro (later), Lit Survey, Gap & RQ, Methodology (Design Science per Penina), Preliminary Results (SE only), Plan (per RQ) | 00:44:37-00:52:17 | Applied | Proposal v0.3 follows this skeleton exactly and states the true status of every chapter.
E14 | Iris/Arnon | Plan in ~3-month semester-aligned blocks over a 3-year horizon - never month-by-month | 00:47:49-00:49:46 | Not started (instructed) | Applies to the Plan chapter, which is not this cycle's deliverable. Recorded so it is not lost.
E15 | Iris | Next steps: Chapter 3 complete; per-RQ literature spreadsheet; think (don't start) §2+§4; share Drive; Word proposal + separate tracking doc; her check-in email; live presentation Aug 12 | 00:49:46-00:56:11 | In progress | See the Deliverables sheet: 5 of 7 delivered by this package; Drive share and email reply are Ali-only.

## Action Items
Action items from the 2026-08-05 call (A08-01 to A08-09)
'Ali only' marks the items nobody else can do: they need Ali's saved draft, his Google account, or his voice.
ID | Owner | Action | Timing | State | Status detail
A08-01 | Ali only | Finalize the RQ/SQ wording from the live-edit session - verify against the saved working draft, not the meeting record | Before Aug 12 | Ali only | BLOCKS Chapter 3 sign-off. Two specific discrepancies now surfaced for this check: 'exploration' vs 'identification/classification' (E6), and 'human' vs 'expert' judgment (E8).
A08-02 | Ali | Write the Gap and Research Questions chapter in full | Aug 12 | Delivered | Complete chapter delivered with the seed-corpus citations attached, construct definitions, falsifiability section and evidence-status table.
A08-03 | Ali | Build a per-RQ literature spreadsheet with an RQ1/RQ2/RQ3/general tagging column | Aug 12 | Delivered | 40 verified sources tagged; plus the per-RQ coverage-gap analysis Iris asked for beyond an inventory, and the frozen search protocol.
A08-04 | Ali | Think about (do NOT start) section 2 (literature survey) and section 4 (research artifact per RQ) | Ongoing | Delivered | Options note: 4 structural options for §2, 9 artifact options across SQ1-SQ3, 14 open questions. No design committed, no search executed.
A08-05 | Ali only | Share the project Drive with Iris and Arnon | Before Aug 12 | Ali only | Requires Ali's Google account. The package folder is populated and ready to share. Also progresses standing controls R-17/A-04/Q-07.
A08-06 | Ali | Maintain the Word proposal AND a separate tracking document | Ongoing | Delivered | Proposal v0.3 (Word) and this tracking workbook are separate artefacts, as instructed.
A08-07 | Iris | Send a check-in email before the Aug 12 meeting | Before Aug 12 | Pending | Iris-side. Ali replies with real status when it arrives - the Deliverables sheet is the honest answer.
A08-08 | Ali | Present progress live at the Aug 12 meeting | Aug 12 | Draft ready | Walkthrough outline and anticipated Q&A prepared; one dry run recommended before the meeting.
A08-09 | Iris/Arnon | Undergraduate team scoping, TA course-pipeline work, Ma'ayanei HaYeshua direction | Ongoing | Not an Ali action | Informational only - recorded so it is not mistaken for an Ali deliverable.

## Deliverables
Aug-12 package contents
Everything marked Delivered exists in this Drive folder. Two items remain that only Ali can complete.
# | Item | State | Purpose
00 | README - Start Here | Delivered | Package index and reading order
01 | Executive Brief (EN + HE) | Delivered | One-page summary of where the work stands
02 | Chapter 3 - Gap and Research Questions | Delivered | THE deliverable for this meeting (A08-02). Full chapter, cited, with evidence-status table
03 | Literature Review - Per Research Question (xlsx) | Delivered | A08-03. 40 tagged sources + per-RQ coverage gaps + frozen search protocol
04 | Progress Presentation | Delivered | Live walkthrough support for A08-08
05 | Requirements and Progress Tracking (xlsx) | Delivered | This workbook - A08-06 tracking half
06 | Sections 2 and 4 - Thinking Notes | Delivered | A08-04. Options only; nothing started
07 | Proposal v0.3 (Word) | Delivered | A08-06 proposal half; carries the D-TITLE-01 decision
08 | Walkthrough Outline + Anticipated Q&A | Delivered | Meeting support; rehearsal aid
-- | Drive shared with Iris and Arnon | Ali only | A08-05 - needs Ali's Google account
-- | Reply to Iris's check-in email | Ali only | A08-07 response - needs Ali

## Decisions Open
Decisions required from the supervisors
These are the questions to work through on Aug 12. Each is stated so it can be answered yes/no or by choosing a named option.
ID | Decision | State | Context and options
D-RQ-01 | Final U-RQ and SQ1-SQ3 wording | Supervisor decision | Verify against Ali's saved working draft (A08-01). Includes: 'exploration' vs 'identification/classification'; 'human' vs 'expert' judgment; whether 'transparently' stays.
D-RQ-02 | Ratify or reverse the E7 leaning (drop auditable/transferable/end-to-end from the headline) | Supervisor decision | Currently applied per the leaning. Formal sign-off outstanding.
D-TITLE-01 | Proposal title | Supervisor decision | v0.2 title still contains 'Reusable', 'Auditable', 'Transferable' - the words the RQ headline dropped. Three candidate titles proposed in the proposal document.
D-DECOMP-01 | Is the three-sub-question decomposition jointly sufficient? | Supervisor decision | None of SQ1-SQ3 takes 'reliability of the co-reasoning' as its object, though the main question names it as the outcome. Raised explicitly in Chapter 3 §3.8 rather than hidden.
D-CH2-01 | Chapter 2 structure | Supervisor decision | Four options prepared (SQ-parallel / community-parallel / lifecycle-stage / hybrid). Choice interacts with the wording sign-off.
D-ART-01 | Artifact granularity and abstraction per study | Supervisor decision | Does each study need exactly one named artifact, or is a package acceptable? Study 3's current 'Core artifact' row lists ten items, several of which are study outputs rather than artifacts.
D-SEARCH-01 | Do QL-01-QL-05 execute before or after the wording sign-off? | Supervisor decision | The queries were frozen against the provisional wording. Coverage analysis also identifies concepts no frozen query covers (e.g. learning-to-defer, LLM uncertainty calibration) - add QL-06+?
D-PRELIM-01 | Which preliminary results may appear in the proposal, and labelled how? | Supervisor decision | Offline replay evidence exists; synthetic fixtures remain protocol-unapproved. Also: is instrument-reliability evidence admissible ahead of EXP-005 labels?

## Evidence Gates
Evidence gates - the counts that bound every claim
These numbers are the honest answer to 'how far along are you'. They are unchanged by this package.
Gate | Current value | State | What it blocks
EXP-005 generalization-safe expert labels | 0 of 24 supplied | Blocked | >=20 required before ANY quantitative accuracy claim; 1-19 would be pilot-only
Medical entry gates G1-G6 | 0 of 6 pass | Blocked | No medical data processing of any kind before all six pass. Internal checkpoint 2026-08-26 decides Plan A vs Plan B
Literature searches QL-01-QL-05 | Protocol ready / NOT run | Open | No novelty or review-completeness statement is permitted until executed, screened and appraised
Accuracy / generalization claims | None made | Verified | Absence of such claims is itself checked by an automated evidence-consistency guard
Clinical performance claims | None made | Verified | No medical performance result exists
RQ/SQ wording | Provisional | Open | Pending A08-01 verification and logged D-RQ-01/D-RQ-02
2026-08-05 meeting record | Machine-derived, speakers inferred | Open | Pending participant confirmation; verbatim attribution not permitted until confirmed