## README
VEGO-AI PhD — Requirements and Progress Tracking
Purpose | The single tracking document requested on the 2026-08-05 call (action A08-06), combined with the complete register of everything the supervisors have asked for across both supervision calls. One row per requirement, action, or open question.
Prepared | 2026-08-11, for the 2026-08-12 supervisor meeting with Prof. Iris Reinhartz-Berger and Prof. Arnon Sturm.
Sheets | 2) Requirements (29 Jul) — R-01..R-19 · 3) Actions (29 Jul) — A-01..A-15 · 4) Open Questions — Q-01..Q-10 · 5) Aug-5 Directives — E1..E15 · 6) Aug-5 Actions — A08-01..09 · 7) Decisions Requested — D-RQ-01..10
How to read status | Green = complete or verified. Amber = working, partial, or awaiting confirmation. Red = open, blocked, or not started. No row is marked complete without recorded acceptance evidence.
Source of record | Rows are extracted programmatically from the tracked records (master traceability register; 2026-08-05 meeting record), not retyped. Status wording is quoted from those records unchanged.
Evidence boundary | This workbook tracks requirements and progress only. It asserts no research result. EXP-005 stands at 0 supplied expert labels (27 blind rows, 24 generalization-safe; the gate needs at least 20). Medical-track readiness stands at 0 of 6 entry gates. No accuracy, generalization, or clinical claim is made anywhere in this package.
Confirmation status | Items derived from the 2026-08-05 call come from a machine transcript with inferred (undiarized) speakers. They are the record's inference and remain pending the participants' own confirmation.

## Requirements (29 Jul)
ID | Control item | Owner | Due date or gate | Deliverable or evidence | Acceptance check | Status | Claim or gate note
R-01 | Use one umbrella PhD question and exactly three related subquestions. | Ali; Iris and Arnon confirm | Working resolution reached 2026-08-05 (informal call, not the rehearsed P-03 presentation); logged decision still outstanding | Approved question block and `three-study-contract.md` | One umbrella question and exactly SQ1–SQ3 appear consistently in the proposal and study contract; supervisor decision is logged. | Working wording refined via 2026-08-05 call; awaiting logged supervisor confirmation | Exact working wording is synchronized and reflects live edits from the 2026-08-05 call, but remains provisional until (a) Ali verifies exact text against his own saved working draft and (b) approval is logged; do not retain competing five- or six-question sets as active outside the documented crosswalk.
R-02 | Map each subquestion to a concrete study, method, evidence/data, and artifact. | Ali; supervisors approve | Before proposal architecture is frozen | `three-study-contract.md` and proposal study table | Every SQ has method, data/evidence, artifact, metrics, contribution, dependencies, fallback, and publication target; no empty required field. | Working; awaiting human confirmation | All study outcomes are `Planned` until executed; medical variants are partner-dependent.
R-03 | Include motivation, literature review, research questions, methodology/artifacts, preliminary results, and work plan/timeline. | Ali | Developed September draft; exact date unverified | Full proposal draft with six-section completeness checklist | All six areas are present, cross-referenced, and traceable to claims, studies, and milestones. | Working; awaiting human confirmation | Preliminary results must remain software/modeling evidence; medicine is not reported as achieved.
R-04 | Demonstrate novelty, doctoral scale, literature positioning, feasibility, available skills/resources, and schedule credibility. | Ali; supervisors judge adequacy | Proposal submission gate | Doctoral-adequacy section, contribution table, feasibility case, resource plan, and schedule | Each adequacy dimension has evidence or a named mitigation; supervisors record accepted or accepted-with-changes. | Working; awaiting human confirmation | Novelty is `Preliminary` until literature synthesis and supervisor review; feasibility cannot rely only on medicine.
R-05 | Prepare a short reviewer-orientation presentation focused on progress and questions, not a duplicate of the proposal. | Ali | After candidacy process and date are formally confirmed | Concise candidacy deck and presenter notes | Deck orients reviewers, summarizes progress/evidence boundaries, names decisions sought, and fits the verified time limit. | Planned; committee process unverified | Do not invent presentation duration, reviewer count, or committee rules.
R-06 | Continue writing and research while reviewer/committee logistics proceed. | Ali | Weekly and ongoing | Dated weekly pre-reads, proposal deltas, and completed artifacts | Every week records completed evidence, one next task, blockers, and proposal text advanced even if administration is pending. | Working; awaiting human confirmation | Administrative uncertainty is not a reason to suspend Plan B work.
R-07 | Keep questions answerable in software/modeling; medicine is a conditional evaluation context. | Ali; supervisors confirm | Next RQ draft and every later revision | Domain-neutral question block and Plan A/Plan B mapping | Each question can be answered by the non-medical baseline and has an optional medical instantiation without changing its scientific meaning. | Confirmed direction; human review pending | No medicine-only doctorate; Plan B is the protected default.
R-08 | Identify current results as software/modeling evidence; medical work remains feasibility or planned evaluation. | Ali; claim-register owner | Before every proposal/report release | Claim register, proposal preliminary-results table, release claim check | Every result has a claim state and source; no clinical or medical performance statement appears without approved evidence. | Confirmed direction; human review pending | EXP-005 remains 0/24; no accuracy/generalization or clinical-performance claim.
R-09 | Do not make feasibility depend solely on medical data, experts, signatures, permissions, or access. | Ali; Iris/Arnon; clinical and governance owners currently unfilled | Before any medical commitment; fallback review by 2026-08-26 | Medical readiness checklist, named owners, RAID entries, Plan B schedule | All six entry gates G1–G6 have documented owners, evidence paths, and feasible completion dates by 2026-08-26; otherwise execution defaults to Plan B. All six must pass before row-level access is considered. | Confirmed risk posture; access unresolved | Data alone is insufficient. Named clinicians, governance, and infrastructure are mandatory.
R-10 | Present Plan A and Plan B with dependencies, decision point, and fallback triggers. | Ali; supervisors confirm | Next proposal iteration; decision checkpoint 2026-08-26 | Proposal alternatives table, fallback rule, RAID decision record | Both plans answer the same questions and preserve doctoral contribution; Plan B activates automatically if any G1–G6 gate lacks an owner, evidence path, or feasible completion date at the checkpoint. | Decisive directive; human review pending | Plan A is medical-enabled and partner-dependent; Plan B is the non-medical execution baseline.
R-11 | Inspect medical resources only enough to understand shape, gaps, and relevance; stop before deep medical study. | Ali | Alongside next RQ draft; before 2026-08-26 decision | Bounded MIMIC/resource sanity-check note with start/stop time, inventory, unknowns, and no data analysis | Note addresses schema/data shape, relevance, missing information, governance questions, and stop condition; no full download or clinical inference. | Partial; bounded audit documented, elapsed time and human review pending | Familiarization does not select MIMIC or authorize use; no raw patient data enters the repo. The audit date/scope is evidenced, but a four-hour elapsed-time claim is not.
R-12 | Keep restricted data in the VDI; use only approved local/offline models; preserve purpose-bound, non-transferable access. | Data controller/security owner unfilled; Ali documents; supervisors accountable for research scope | Before any restricted-data experiment | Approved data-flow/security note, access register, local-model approval, and proposal constraint statement | Authorized owner confirms storage, access, model, logging, retention, and export rules; technical runbook passes review before execution. | Constraint; institutional details unverified | Meeting statements are not an independently verified Clalit policy; fail closed until written approval.
R-13 | Hold short, task-focused weekly meetings with completed work, one next task, and writing progress. | Iris/host for invite; Ali for pre-read; Iris and Arnon for decisions | Weekly; Wednesday 09:00 series confirmed | Recurring VEGO series accepted by Ali, Iris, and Arnon, plus completed `weekly-supervisor-pre-read.md` per meeting | Recurrence is visible and accepted; each future meeting must still close with one accepted task, owner, due date, and decision read-back. | Calendar confirmed; weekly execution ongoing | Recurrence is established; the task-focused pre-read/closeout discipline remains an ongoing acceptance check.
R-14 | Deliver RQ hierarchy, related-work scope, review start, Excel template, and seed papers. | Ali | Next confirmed supervisor meeting | Working hierarchy and study contract; [native literature Sheet](https://docs.google.com/spreadsheets/d/1tVAM10bxlmL7_8SbgDgN5BRfAR2f5Q4pGvQmx-Ypp4A/edit) with six seed rows; remaining package links | All five artifacts open successfully; the search is started and evidenced; no fabricated minimum count; supervisors receive the package only after Ali’s review. | Partially implemented; not sent or approved | Sheet/template existence is established; search execution, package review, sending, and supervisor acceptance remain open.
R-15 | Maintain one paper per Excel row with bibliographic, study/evidence, and researcher-synthesis field groups. | Ali | Initial template/seed tranche implemented; then ongoing | [Native literature Sheet](https://docs.google.com/spreadsheets/d/1tVAM10bxlmL7_8SbgDgN5BRfAR2f5Q4pGvQmx-Ypp4A/edit) in `03_Literature_Review`: six tabs, five native tables/dropdowns, six seeded paper rows | Initial workbook structure and seed rows exist; final taxonomy, row-level source verification, and ongoing screening must still pass validation. | Initial workbook tranche implemented; ongoing | Artifact existence does not establish literature completeness, novelty, or verified paper conclusions.
R-16 | Keep the matrix current, group papers, expose gaps, and link gaps to contributions. | Ali; supervisors review synthesis | Ongoing; weekly update during active review | Same native Sheet; `Search_Log` protocol is ready; synthesis/gap views and execution evidence remain required | Searches are executed and logged; screened/included rows are updated; each category has synthesis, limitations, gap status, and proposal-use mapping. | Ongoing; Search_Log ready, searches not executed | Novelty stays `Preliminary` until the corpus, screening, and synthesis are completed and reviewed.
R-17 | Use a meaningful shared PhD workspace; keep the shared MIMIC/source area read-only and work separately. | Ali for working area; Iris/resource owner for source share | Before next meeting | [Private Ali-owned Drive root](https://drive.google.com/drive/folders/1Och2Vlux87uqk6QZy0F4xr2WhfzY_cd-) with all nine specified subfolders; source/working separation; [3 August metadata/ACL/authorization split](../governance/drive-boundary-verification-2026-08-03.md); future recipient access-test evidence | Private structure exists; Ali must approve sharing; supervisors must pass access tests; observable source metadata must remain consistent; ACL/viewer-only state and named-user authorization must be independently verified; no sensitive data enters an unapproved location. | Private working structure implemented; metadata inventory corroborated; source ACL, research authorization, supervisor sharing/access pending | The root has not been shared externally; no package-sent or supervisor-access claim is allowed. Metadata visibility and download capability do not prove viewer-only ACL or research-use authorization.
R-18 | Produce a developed September draft and target full submission by early October/pre-October, subject to official confirmation. | Ali; supervisors; Graduate Studies confirms formal dates | September draft; early October working target | Baseline schedule, weekly milestone evidence, formal-deadline confirmation | Draft and submission checkpoints are dated; official dates are cited from an authoritative source; variance is logged and mitigated. | Working target; formal deadline unverified | The plan may use internal dates but must label them working targets until A-14 closes.
R-19 | Complete the course work and trace reusable outputs into the proposal. | Ali | Course and proposal schedule; exact course date unverified | Course presentation/written survey plus proposal reuse map | Course deliverables exist; every reused figure, synthesis, taxonomy, or paragraph has provenance and is adapted to the proposal rather than copied blindly. | Working; exact due date unverified | Course work can support literature positioning but does not itself establish novelty or system performance.

## Actions (29 Jul)
ID | Control item | Owner | Due date or gate | Deliverable or evidence | Acceptance check | Status | Claim or gate note
A-01 | Draft one main RQ, three SQs, and the study/method/artifact map. | Ali | Next confirmed meeting | Question block and `three-study-contract.md` | Exactly three SQs; all study-contract fields populated; supervisor review requested. | Draft prepared; package review/delivery and supervisor decision pending | Wording and mapping remain provisional until a decision is logged.
A-02 | Define related-work types and begin the review. | Ali | Next confirmed meeting | `Search_Log` protocol in the [native literature Sheet](https://docs.google.com/spreadsheets/d/1tVAM10bxlmL7_8SbgDgN5BRfAR2f5Q4pGvQmx-Ypp4A/edit), taxonomy, and future executed searches | Protocol fields are ready; databases/queries are actually run and dated; screening and synthesis evidence is recorded. | Partially implemented; protocol ready, searches not executed | No literature finding or novelty conclusion may be inferred from a ready protocol alone.
A-03 | Build and seed the Excel literature matrix. | Ali | Initial tranche complete; ongoing screening/search by next checkpoint | [Native literature Sheet](https://docs.google.com/spreadsheets/d/1tVAM10bxlmL7_8SbgDgN5BRfAR2f5Q4pGvQmx-Ypp4A/edit): six tabs, five native tables/dropdowns, six seeded paper rows | Initial template/seed tranche exists; sources and row completeness are validated during ongoing screening; authors’ conclusions remain separate from Ali’s synthesis. | Initial template/seed tranche implemented; ongoing | Do not fabricate missing paper details or treat seed rows as a completed review.
A-04 | Create the separate shared PhD working area, upload current outputs, and confirm access. | Ali | Before next confirmed meeting | [Private Drive root](https://drive.google.com/drive/folders/1Och2Vlux87uqk6QZy0F4xr2WhfzY_cd-) with nine specified subfolders; future sharing and access-test evidence | Structure exists privately; Ali reviews contents/permissions, then Iris and Arnon can open expected artifacts; source and working folders remain distinct. | Private structure implemented; supervisor sharing/access pending | Not shared externally; no source edits, sensitive-data upload, package-sent, or supervisor-access claim.
A-05 | Share MIMIC index, CSV/schema, guideline, and class-diagram resources with viewer access. | Iris/resource-providing speaker | Reported during/after call; receipt verification immediate | Source-folder URL, item inventory, permission test | Ali can view named resources; no edit rights are required; owner and usage restrictions are recorded. | Reported sent; receipt unverified | Access is not approval to copy, process, or publish.
A-06 | Finalize weekly Wednesday 09:00 invitations and move conflicts. | Iris/host | Completed; maintain weekly | Recurring VEGO calendar series accepted by Ali; Iris and Arnon accepted | Recurrence, participants, timezone, and next occurrence are visible and accepted. | Complete; recurrence confirmed | Calendar acceptance is established; individual meeting outcomes still require weekly records.
A-07 | Report completed work, choose one next task, and advance writing every week. | Ali; Iris and Arnon | Weekly | Completed weekly pre-read and decision/change log | Previous task is accepted/rejected with evidence; exactly one priority task has owner, due date, and definition of done. | Accepted in principle | Progress claims require links or reviewed artifacts.
A-08 | Perform a bounded MIMIC/medical-resource inspection and document shape, gaps, relevance, and stop point. | Ali | Alongside next RQ draft; before 2026-08-26 | Time-boxed sanity-check note | Inspection stays metadata/schema-first; records unknowns and stop decision; no prohibited download, clinical inference, or model use. | Partial; metadata/schema audit documented, elapsed-time record and review pending | MIMIC remains exploratory, not selected. Do not claim four elapsed hours without a timing record.
A-09 | Validate medical field/route, named experts, data, permissions, and access. | Iris and Arnon; clinical/governance owners unfilled | Before medical commitment; mandatory review 2026-08-26 | Signed six-gate readiness scorecard and partner/governance evidence | G1–G6 each have a documented owner, evidence path, and feasible completion date at the checkpoint; otherwise Plan B activates. All six pass before row-level access is considered. | Open | Partner-dependent; silence or verbal optimism does not satisfy a gate.
A-10 | Draft Plan A and Plan B with explicit fallback triggers. | Ali; supervisors confirm | Next proposal iteration | Proposal alternatives section and decision rule | Both plans answer the same RQs, have viable study/data paths and publication outputs, and state the 2026-08-26 automatic fallback. | Partial; plans and trigger drafted, acceptance and Plan B resource route pending | Plan B must be executable without medical access.
A-11 | Document VDI/privacy/local-LLM constraints and later inventory approved local models. | Ali; data/security owner unfilled | Constraint now; model selection before restricted processing | Proposal constraint paragraph, data-flow checklist, approved-model register | Authorized owner confirms environment and model; no online/commercial endpoint can receive restricted content. | Partial; constraint documented, authority/environment/model evidence pending | Fail closed; no model is “approved” by technical suitability alone.
A-12 | Produce a developed proposal draft for supervisor feedback. | Ali | September working target; exact date unverified | Full draft and completeness/claim checks | Six required sections are complete enough for substantive review; all open decisions and claim states are visible. | Open | Date remains internal until A-14 confirms formal schedule.
A-13 | Work toward full proposal submission by early October/pre-October. | Ali; supervisors | Early October working target; formal date pending | Submission-ready package and authoritative deadline evidence | Supervisor-approved package meets verified institutional checklist and is submitted through the authorized route. | Open | Do not report “submitted” without receipt evidence.
A-14 | Confirm candidacy deadline, reviewer count, nomination process, and committee rules. | Ali initiates; supervisors and Graduate Studies confirm | Before treating process guidance as policy | Written response or authoritative university source with date and owner | All four process fields have cited authoritative answers; contradictions with the work plan are reconciled in the change log. | Open | Meeting statements remain guidance, not policy.
A-15 | Keep Ali in the Clalit/innovation-partner loop and clarify the next external meeting. | Iris/team | Immediate/next partner contact | Meeting invitation/minutes, partner map, and use-case request | Ali is included; date, attendees, partner identity, purpose, questions, decisions, and next owner are recorded. | Committed in principle; scheduling open | No partner commitment or access is established until written evidence exists.

## Open Questions
ID | Control item | Owner | Due date or gate | Deliverable or evidence | Acceptance check | Status | Claim or gate note
Q-01 | What is the final umbrella-question and SQ1–SQ3 wording? | Ali drafts; Iris and Arnon decide | Held 2026-08-05 (informally); logged decision still outstanding | Decision-log entry and approved question block | Decision records exact wording, rationale, approvers, date, and affected documents. | Working answer exists from the 2026-08-05 call; not yet a logged decision | Working wording in the study contract now reflects the 2026-08-05 call, but this is still not supervisor approval — a logged decision with exact wording, rationale, and approver names is required to close this row.
Q-02 | Will medicine be used, and which field/collaboration route will be selected? | Iris, Arnon, partner/clinical lead unfilled | Before medical commitment; default review 2026-08-26 | Route decision and six-gate readiness evidence | G1–G6 readiness is documented by the checkpoint and all six gates must pass before row-level access; otherwise Plan B is recorded. | Open | Partner-dependent; default is Plan B at the checkpoint.
Q-03 | What differentiates Plan A and Plan B, and what triggers fallback? | Ali proposes; supervisors decide | Next proposal iteration; no later than 2026-08-26 | Alternatives table and signed decision/change entry | Plans share scientific questions and contribution; mandatory gates and automatic fallback are explicit. | Open; internal default defined | Internal control defines Plan A as medical-enabled and Plan B as non-medical; supervisor confirmation remains pending.
Q-04 | What are the final literature categories and synthesis columns? | Ali proposes; supervisors review | Next confirmed meeting | Workbook data dictionary and taxonomy decision | Categories cover core human-AI, agentic/HITL, governed reuse, evaluation, software/modeling, and conditional medical work; column definitions are unambiguous. | Open | Taxonomy changes must preserve author/researcher separation.
Q-05 | Is MIMIC selected, and what license, access, privacy, and ethics rules apply? | Data owner/governance authority unfilled; supervisors | Before experiment design | Authoritative license/access/ethics determination and dataset decision | Owner, permitted purpose, users, storage, transformations, exports, retention, and publication rules are documented; selection is explicitly accepted or rejected. | Open | Viewer access is not selection or permission to process.
Q-06 | Which local/offline LLMs are institutionally approved and technically suitable? | Data/security authority and technical owner unfilled | Before any restricted-data model use | Approved-model register and offline verification | Model/runtime is named, approved in writing, tested with network disabled, and operated under documented access/logging rules. | Open | No commercial or connected model receives restricted data.
Q-07 | Are Wednesday 09:00 meetings and Drive permissions active? | Iris/host; Ali verifies; Arnon confirms | Immediate | Recurring VEGO calendar series accepted by all three participants; private Drive root exists but is not externally shared | Calendar portion passes; Drive portion closes only after Ali authorizes sharing and Iris/Arnon pass access tests; source remains viewer/read-only. | Partially resolved: calendar confirmed; Drive access pending | Do not conflate calendar acceptance with supervisor access to the private Drive or package delivery.
Q-08 | What are the official dates, reviewer count, nomination process, and committee rules? | Graduate Studies/university; Ali and supervisors | Before formal scheduling or submission claim | Authoritative dated response and reconciled schedule | All requested fields are answered from an official source and reflected in proposal/calendar controls. | Open | Formal policy must not be reconstructed from the transcript.
Q-09 | What exact research use case and access prerequisites should be submitted to Clalit? | Iris/Arnon/clinical lead unfilled; Ali drafts | Before advancing partner request | One-page use-case brief and prerequisite checklist | Brief states problem, users, data minimum, human role, output, evaluation, environment, risks, exclusions, and requested decision. | Open | Access expected in conversation is not provisioned access.
Q-10 | Was the proposed Clalit meeting accepted, and what are the retrieval mechanism and second partner? | Iris/team | Before treating opportunity as committed | Confirmed invitation/minutes and partner/mechanism record | Meeting status, identities, roles, mechanism meaning, decisions, and next steps are documented by an accountable participant. | Open | Unclear transcript terminology must be human-corrected before use.

## Aug-5 Directives
ID | What was asked for | Attributed to (inferred) | Record status | Timestamp | Affected artifact(s)
E1 | Move from a statement of intentions to an actual thesis proposal soon; time is tight. | Iris | `Confirmed directive` | `00:00:08-00:00:35` | Proposal draft
E2 | Parallel tracks in progress: same-day Soroka meeting; a prospective 3-student undergraduate project team; VEGO-AI being integrated into Iris's course by a summer TA (possibly "Matan") rebuilding the pipeline for mandatory human review at every step, against a free/no-cost LLM API; a third hospital contact, Ma'ayanei HaYeshua. | Iris | `Discussion or proposal` | `00:00:35-00:03:52` | PhD trajectory; course integration
E3 | Draft main RQ and 3 sub-questions presented as: (main) capturing/governing reusable human judgment for Agentic-AI assessment via local LLM, producing reviewable AI/human core-reasoning; (SQ1) selective human involvement; (SQ2) reuse of governed/validated knowledge without overfitting; (SQ3) evaluation/transfer, including toward medical. | Ali | `Confirmed directive`; `Needs transcript verification` | `00:06:04-00:10:59` | Proposal draft; RQ decision pack
E4 | The draft conflates the proposed Agentic-AI *solution* with the actual *research question*; too much verbal padding, not sharp enough yet. Distinguish the core question (e.g. ability to identify variability) from technical/implementation aspects. | Arnon | `Confirmed directive` | `00:11:01-00:13:07` | RQ decision pack
E5 | Remove "reused" from the main RQ; it belongs to how knowledge is generalized/folded back in, which is a sub-question concern, not the headline question. | Iris | `Confirmed directive`; `Needs transcript verification` | `00:13:39-00:15:09` | Main RQ wording
E6 | Main RQ is currently too broad (general domain-specific artifacts / human-AI reasoning); narrow it explicitly to variability identification/classification. | Iris, echoing Arnon | `Confirmed directive`; `Needs transcript verification` | `00:15:10-00:17:23` | Main RQ wording
E7 | Working direction for main RQ assembled live (see `docs/video1638342429.transcript.en.md` §5); keep "reliable," lean toward dropping "auditable"/"transferable"/"end-to-end" from the headline; insert "variability exploration scenarios" into SQ1, otherwise keep SQ1 close to original. | Iris, Arnon, Ali | `Confirmed directive`; `Needs transcript verification` | `00:26:29-00:29:27` | Main RQ + SQ1 wording
E8 | Split SQ2 conceptually into (a) what the human says and how it's captured, and (b) how that transfers to future cases. Debate on "expert" vs. "human" wording; leans "expert" - physicians specifically in the medical domain, course/team-level rigor in the SE domain. | Iris, Arnon | `Confirmed directive`; `Open choice`; `Needs transcript verification` | `00:29:27-00:36:29` | SQ2 wording
E9 | Tie SQ2 explicitly to "core reasoning" (present in main RQ but otherwise unaddressed by any sub-question); add an evaluation-criteria clause to SQ2, matching SQ1/SQ3's style (balance correctness vs. completeness; avoid unsafe generalization or loss of human authority). | Iris | `Confirmed directive`; `Needs transcript verification` | `00:41:31-00:44:02` | SQ2 wording
E10 | SQ3 wording "looks good" as drafted; mild, non-critical discomfort with the word "transparently." | Iris | `Confirmed directive`; `Open choice` | `00:39:20-00:41:00` | SQ3 wording
E11 | Explains starting deliberately from the SE domain, not medical, because domain-transfer behavior is unproven; gives Clalit chronic-pain vs. Soroka AMD as maximally-different domain examples motivating caution about generalization claims. | Iris | `Discussion or proposal` | `00:37:19-00:39:20` | Research methodology; domain framing
E12 | Refine SQ3: uncertainty in transferring "user involvement" patterns is often but not always domain-driven (e.g. failure to define actors/use-cases is a general capability gap, not domain-specific); SQ3 should focus on classifying domain-specific vs. broadly reusable/transferable elements. | Arnon | `Confirmed directive` | `00:52:17-00:53:54` | SQ3 wording
E13 | Confirmed proposal chapter structure: Introduction (write later); Literature Survey; Gap & Research Question (drafted); Research Methodology (Design Science per Prof. Penina's course - per-RQ study/artifact/design/evaluation, covering both SE and medical domain context/challenges); Preliminary Results (SE-domain-only so far; medical = infrastructure-building only); Plan (per-RQ). RQs themselves are not written to be domain-specific. | Iris | `Confirmed directive` | `00:44:37-00:52:17` | Proposal structure
E14 | Plan/timeline must not be month-by-month (too low-resolution, unrealistic to maintain); use ~3-month blocks aligned to semester boundaries; horizon is a 3-year plan (Arnon confirms 3, not 2), understood as a baseline subject to change. | Iris; confirmed by Arnon | `Confirmed directive` | `00:47:49-00:49:46` | Plan section
E15 | Next-step assignments: finish the Gap+RQ chapter fully; build a per-RQ literature spreadsheet (with an RQ1/RQ2/RQ3/general tag column); think about (but do not yet start) sections 2 (lit survey) and 4 (research artifact per RQ); share the Drive; keep a Word proposal doc plus a separate tracking doc; Iris sends a check-in email before the Aug 12 meeting; Ali presents progress live at that meeting; next meeting **Wednesday 2026-08-12, 09:00**, goal = Chapter 3 complete. | Iris | `Confirmed directive` | `00:49:46-00:56:11` | Next-step plan; calendar

## Aug-5 Actions
ID | Action | Owner (inferred) | Timing | Evidence | Confirmation status
A08-01 | Finalize the wording of the main RQ and SQ1-SQ3 from the live-edit session (verify against saved working draft, not this record). | Ali | Before Aug 12 | `00:13:07-00:44:37` | Pending
A08-02 | Write the "Gaps and Research Questions" chapter/section in full. | Ali | Aug 12 meeting | `00:49:46-00:50:06` | Pending
A08-03 | Build a literature spreadsheet: relevant sources per RQ1/RQ2/RQ3/general, with a tagging column. | Ali | Aug 12 meeting | `00:50:06-00:53:00`; `00:56:0x` | Pending
A08-04 | Think about (do not yet execute) section 2 (literature survey) and section 4 (research artifact per RQ - what exactly each artifact is). | Ali | Ongoing toward Aug 12+ | `00:54:38-00:55:11` | Pending
A08-05 | Share the project Drive with Iris and Arnon. | Ali | Before Aug 12 | `00:55:11-00:55:30` | Pending
A08-06 | Maintain two documents: the Word proposal, and a separate tracking/status document. | Ali | Ongoing | `00:55:30-00:56:04` | Pending
A08-07 | Send a check-in email early the following week, before the Aug 12 meeting. | Iris | Before Aug 12 | `00:56:04-00:56:11` | Completion not evidenced by this recording
A08-08 | Present progress live at the Aug 12 meeting. | Ali | Aug 12 meeting | `00:56:08-00:56:11` | Pending
A08-09 | Undergraduate project team scoping, TA course-pipeline work, Ma'ayanei HaYeshua direction - Iris/Arnon-side, informational to Ali. | Iris/Arnon | Ongoing | `00:00:35-00:03:52` | Not an Ali action item

## Decisions Requested
ID | Decision | Priority | Outcome | Approvers
D-RQ-01 | Umbrella research-question wording | Mandatory | Pending | Iris and Arnon
D-RQ-02 | SQ1, SQ2, and SQ3 wording | Mandatory | Pending | Iris and Arnon
D-RQ-03 | Three-study mapping and method direction | Mandatory | Pending | Iris and Arnon
D-RQ-04 | Plan A as conditional medical transfer; Plan B as complete non-medical route | Mandatory | Pending | Iris and Arnon
D-RQ-05 | Every research question remains answerable under Plan B | Mandatory | Pending | Iris and Arnon
D-RQ-06 | 26 August as the medical fallback control date | Time permitting | Pending | Iris and Arnon
D-RQ-07 | Evidence-boundary wording and the five claim states | Mandatory | Pending | Iris and Arnon
D-RQ-08 | Initial literature scope and taxonomy direction | Time permitting | Pending | Iris and Arnon
D-RQ-09 | Bounded metadata/schema MIMIC boundary; continued no-row inspection | Time permitting | Pending | Iris and Arnon
D-RQ-10 | Owners for medical feasibility and university-process verification | Assignment | Pending | Iris and Arnon
Note | Outcomes are recorded only from an explicit supervisor decision in the meeting. Silence or ambiguity is recorded as Deferred, never as approval. D-RQ-01 and D-RQ-02 were discussed informally on 2026-08-05 but are not yet logged decisions.