2026-08-12 Supervisor Package

# 2026-08-12 Supervisor Package — Start Here

Meeting: Wednesday 2026-08-12, 09:00 · Participants: Prof. Iris Reinhartz-Berger, Prof. Arnon, Ali Hamed Purpose: deliver the next-step package agreed on 2026-08-05 (E15), with Chapter 3 complete.

## What you asked for on 5 August, and where it is

| # | Your request (E15 / A08-…) | Delivered? | Where |
| --- | --- | --- | --- |
| 1 | Finish the Gap and Research Questions chapter in full | Yes | 02 - Chapter 3 |
| 2 | Build a per-RQ literature spreadsheet with an RQ tag column | Yes | 03 - Literature Review |
| 3 | Think about (do not start) §2 and §4 | Yes — thought about, not started | 06 - Sections 2 and 4 - Thinking Notes |
| 4 | Share the Drive with Iris and Arnon | Ali-only step | this folder is ready to share |
| 5 | Keep a Word proposal plus a separate tracking doc | Yes, both | 07 - Proposal v0.3 and 05 - Requirements and Progress Tracking |
| 6 | Iris sends a check-in email | Awaiting | reply prepared from 05 |
| 7 | Present progress live on Aug 12 | Ready | 04 - Progress Presentation, 08 - Walkthrough and Q&A |

## Reading order (if you have 10 minutes)

`01 - Executive Brief` — one page, where the work stands.

`02 - Chapter 3` — the deliverable. If you read one thing, read §3.2 (positioning table) and §3.3 (the gap).

`05 - Requirements and Progress Tracking` → *Decisions Open* — the eight decisions I need from you.

## Full contents

| File | What it is |
| --- | --- |
| 00 - README - Start Here | This file |
| 01 - Executive Brief (EN + HE) | One-page status summary |
| 02 - Chapter 3 - Gap and Research Questions | The deliverable (A08-02) — full chapter, cited |
| 03 - Literature Review - Per Research Question | A08-03 — 40 tagged sources, per-RQ coverage gaps, frozen search protocol |
| 04 - Progress Presentation | Slides supporting the live walkthrough |
| 05 - Requirements and Progress Tracking | A08-06 tracking half — requirements, actions, deliverables, open decisions, evidence gates |
| 06 - Sections 2 and 4 - Thinking Notes | A08-04 — options only; nothing started |
| 07 - PhD Research Proposal v0.3 (Word) | A08-06 proposal half — chapter skeleton with true status per chapter |
| 08 - Walkthrough and Anticipated Q&A | Running order and honest answers to the hard questions |

## Three things worth knowing before the meeting

1. Chapter 3 is now cited. The earlier draft asserted gaps without references. This version positions four bodies of work against the gap using a verified seed corpus — the reference list of our own MODELS/MAS4Models submission plus the tracked resource pack — and marks every "no established approach does X" as a candidate claim for the unrun searches to confirm or refute.

2. Two wording discrepancies are flagged, not resolved. I could not tell from the recording which wording was agreed, so I did not choose silently:

E6 is recorded as narrowing the question to variability identification/classification; the

reconstructed wording says variability exploration. These are not synonyms.

The main question and SQ1 say human judgment; SQ2 and SQ3 say expert judgment.

Both need my saved working draft (A08-01) and your ruling.

3. The evidence position has not moved — and the chapter says so in a table. EXP-005: 0 of 24 generalization-safe expert labels. Medical entry gates: 0 of 6. Literature searches: protocol-ready, not run. No accuracy, generalization, clinical-performance or effort-reduction claim appears anywhere in this package.

## Status of this package

Everything here is a working draft for review, not an approved artefact. The 2026-08-05 meeting record it traces to is machine-transcribed with inferred speakers and is itself pending your confirmation; every reference to it carries an E-identifier so you can check it in one step. Nothing is marked approved merely because it is consistent with a draft.