Executive Brief

# Executive Brief — 2026-08-12 Supervisor Meeting

Ali Hamed · PhD-track proposal · for Prof. Iris Reinhartz-Berger and Prof. Arnon

## In one paragraph

Chapter 3 (Gap and Research Questions) is complete and, unlike the previous draft, grounded in citations: it positions four bodies of work, states for each what it establishes and what it leaves open, and defines the two constructs the thesis depends on. The per-RQ literature spreadsheet is delivered with 40 verified sources plus the per-question coverage-gap analysis — the part beyond a plain inventory. Sections 2 and 4 were thought about and deliberately not started, as instructed; the thinking is delivered as options with trade-offs. The Word proposal and a separate tracking document are both maintained. The evidence position is unchanged and stated plainly: 0 of 24 expert labels, 0 of 6 medical gates, searches not run — and no claim in this package depends on any of them.

## The three headlines

1. The gap now has a shape you can attack. Automated assessment detects deviations but does not interpret them. Agentic-assistance research shows expert correction is needed but treats it as a one-off repair. Human-in-the-loop research gives mechanisms but no selection policy under a bounded attention budget. Variability engineering formalises designed variability, not the observed interpretive kind at issue here. The connection between them — when to ask, what to keep, where it may be reused — is where the open questions sit.

2. Two wording questions came back unresolved, deliberately. The recording is machine-transcribed with inferred speakers, so it cannot settle exact wording. Rather than choose silently I flagged both: exploration vs identification/classification in the main question (E6), and human vs expert judgment across the question set (E8). Both need my saved draft and your ruling.

3. Eight decisions are waiting for you — listed in the tracking workbook. The first three (final wording, title, decomposition sufficiency) block everything downstream.

## What is complete, what is not, and why

|  | Status | Why |
| --- | --- | --- |
| Chapter 3 | Complete | The deliverable you set for today |
| Per-RQ literature spreadsheet | Complete | 40 sources tagged + coverage gaps + frozen protocol |
| §2 and §4 | Deliberately not started | Your instruction: think, don't start |
| Chapters 1, 4, 6 | Not started | E13 sequencing — Introduction is written last |
| Chapter 5 | Status only | Software/modelling mechanism evidence; no results chapter yet |

## The honest constraint

The binding constraint is not writing or engineering: it is independent expert labels. EXP-005 needs ≥20 generalization-safe labels for any quantitative claim and currently has 0 of 24. That needs two independent reviewers and an adjudicator — a resourcing question, not a build task, and it is on the decisions list.

## Notable finding from the coverage analysis

The seed corpus contains no design-science methodology sources — despite the methodology chapter being design-science-based per your E13 confirmation. That is a concrete, fixable hole and it is now visible rather than latent.

## תקציר מנהלים — בעברית

פרק 3 (פער ושאלות מחקר) הושלם, וכעת הוא מעוגן במקורות: הוא ממקם ארבעה גופי ידע, מציין לכל אחד מה הוא מבסס ומה נותר פתוח, ומגדיר את שני המושגים שעליהם התזה נשענת. גיליון הספרות לפי שאלת מחקר הוגש עם 40 מקורות מאומתים ועם ניתוח פערי הכיסוי לכל שאלה — החלק שמעבר לרשימה בלבד. סעיפים 2 ו-4 נחשבו ולא הוחלו, בדיוק לפי ההנחיה; החשיבה מוגשת כאפשרויות עם יתרונות וחסרונות. מסמך ההצעה בוורד ומסמך המעקב הנפרד — שניהם מתוחזקים.

מצב הראיות ללא שינוי ומוצג במפורש: 0 מתוך 24 תיוגי מומחה, 0 מתוך 6 שערים רפואיים, חיפושי הספרות לא הורצו. אף טענה בחבילה הזו אינה נשענת עליהם.

שתי שאלות ניסוח חזרו ללא הכרעה, במכוון — ההקלטה היא תמלול מכונה עם זיהוי דוברים משוער ואינה יכולה לקבוע ניסוח מדויק: exploration מול identification/classification בשאלה הראשית, ו-human מול expert לאורך מערך השאלות. שתיהן דורשות את הטיוטה השמורה שלי ואת הכרעתכם.

המגבלה הכנה: החסם אינו כתיבה או פיתוח אלא תיוגי מומחה בלתי תלויים — נדרשים לפחות 20 ויש 0. זו שאלת משאבים (שני בודקים ומכריע), לא משימת בנייה.